## Sheet1
Task | Subtask | Effort Estimate (Story Points)
Project Setup | Create new Java project repository | 2
| Set up project structure and directories | 3
| Configure build tools and dependencies | 2
| Initialize Git repository | 1
Adapter Blueprint | Define adapter service requirements and goals | 2
| Identify necessary dependencies and frameworks | 3
| Design project architecture and components | 5
| Define API contracts and payload structures | 3
| Implement basic project structure | 2
Initial Commit | Add project files to Git repository | 1
| Perform initial commit | 1
| Push code to development environment | 1
Integration Testing | Write unit tests for project setup and configuration | 2
| Conduct integration tests for initial functionality | 3
Documentation | Document project setup and configuration steps | 2
| Update project README with relevant information | 2
NAS Integration | Configure NAS mount point | 2
| Establish connection to NAS | 3
| Verify NAS accessibility and permissions | 1
Fetch Pain File | Identify file location on NAS | 2
| Implement file retrieval mechanism | 5
| Handle error scenarios and exception handling | 3
Integration Testing | Write unit tests for NAS integration | 2
| Conduct integration tests for file retrieval | 3
Documentation | Document NAS integration process and steps | 2
| Create user guide for file retrieval | 2
Task | Subtask | Effort Estimate (Story Points)
Scheduler Configuration | Configure Spring scheduler in the project | 3
| Define a scheduled task to pick file from NAS mount | 3
| Set up scheduler interval for every 3 hours | 2
NAS Mount Path Configuration | Define and configure NAS mount path property | 2
| Read NAS mount path from configuration | 2
| Validate and handle incorrect or missing path | 2
File Retrieval | Implement file retrieval logic | 5
| Handle errors and exceptions during file retrieval | 3
Error Handling | Implement retry mechanism for failed attempts | 3
| Log error details for troubleshooting and monitoring | 2
Testing | Write unit tests for scheduler and file retrieval | 3
| Perform integration tests for scheduled file picking | 3
Documentation | Document scheduler setup and configuration steps | 2
| Update project README with scheduler information | 2
XML to JSON Mapping | Implement XML to JSON mapping logic | 5 | 2 days
Handle field mappings and transformations
Convert XML to JSON structure
JSON Validation | Define validation rules for GPS JSON request | 3 | 1 day
Implement JSON validation logic
Validate mapped JSON request against defined rules
Encoding | Determine appropriate encoding method for the JSON request | 2 | 0.5 day
Implement encoding logic for the JSON request
Testing | Write unit tests for XML to JSON mapping and validation | 3 | 1 day
Perform integration testing of mapping and validation
Documentation | Document XML to JSON mapping and validation process | 2 | 0.5 day
EMS Queue Setup | Research and choose a suitable JMS library | 2 | 1 day
| Set up and configure EMS queue | 3
Message Publishing | Implement logic to publish the JSON request to EMS queue | 5 | 2 days
Establish connection to EMS queue
Convert JSON request to message format
Publish the message to the EMS queue
Message Consumption | Implement logic to consume messages from EMS queue | 5 | 2 days
Establish connection to EMS queue
Retrieve and process messages from the EMS queue
Handle message acknowledgement and error handling
Testing | Write unit tests for EMS queue integration | 3 | 1 day
Perform integration tests for message publishing/consumption
Documentation | Document EMS queue setup and integration process | 2 | 0.5 day
EMS Connection Setup | Establish connection to the EMS queue | 3 | 1 day
Configure connection parameters
Message Preparation | Retrieve the JSON request data | 2 | 0.5 day
Convert JSON request to message format
Set message headers and properties
Message Publishing | Publish the message to the EMS request queue | 5 | 2 days
Handle message publishing errors and retries
Implement message batching or asynchronous publishing if needed
Testing | Write unit tests for message publishing | 3 | 1 day
Perform integration tests for message publishing
Documentation | Document the process of publishing a message to the EMS queue | 2 | 0.5 day
Task | Subtask | Effort Estimate (Story Points) | Timeline
EMS Connection Setup | Establish connection to the EMS response queue | 3 | 1 day
Configure connection parameters
Message Consumption | Retrieve messages from the EMS response queue | 5 | 2 days
Handle message deserialization and conversion
Process and validate the received response
Implement message acknowledgment and error handling
Message Processing | Extract relevant data from the response message | 3 | 1 day
Perform necessary transformations or data manipulations
Update application state or trigger further actions
Testing | Write unit tests for message consumption and processing | 3 | 1 day
Perform integration tests for message consumption
Documentation | Document the process of consuming and processing EMS response | 2 | 0.5 day