## Sheet1
Story | Task | Subtask | Effort Estimate | Effort Estimate (Story Points) | Timeline | Status | Developer
Infra setup | Infra setup | Create RPS Java project repository |  |  |  | Done
SFX and NAS mount Creation
DEV, UAT, non-prod and Prod env. Setup
Create Blueprint of Java Adapter Service and Initial Commit on Dev | Adapter Blueprint | Identify necessary dependencies and frameworks | 2 | 11
|  | Define API contracts and payload structures | 3
|  | Implement basic project structure | 3
|  | Update project README with relevant information | 1
| Initial Commit | Perform initial commit, Push code to development environment | 2
NAS mount integration and pick file from NAS mount | NAS Integration | Configure NAS mount point | 2 | 22
|  | Establish connection to NAS | 3
|  | Read NAS mount path from configuration, Validate and handle incorrect or missing path | 5
|  | Verify NAS accessibility and permissions | 1
| Fetch Pain File | Identify file location on NAS | 2
|  | Implement file retrieval mechanism | 5
|  | Handle error scenarios and exception handling | 4
Implement a spring scheduler in adapter service | Scheduler Configuration | Configure Spring scheduler in the project | 3 | 25
|  | Define a scheduled task to pick file from NAS mount | 4
|  | Set up scheduler interval ….. | 2
| Error Handling | Implement retry mechanism for failed attempts | 5
|  | Log error details for troubleshooting and monitoring | 2
| Testing | Write unit tests for scheduler and file retrieval | 4
|  | Perform integration tests for scheduled file picking | 4
|  | Update project README with scheduler information | 1
Implement XML pain file field map with GPS json request structure and validation (logic for XML to json mapping) | XML to JSON Mapping | Implement XML to JSON mapping logic | 8 | 34
|  | Handle field mappings and transformations | 6
|  | Convert XML to JSON structure | 2
| JSON Validation | Define validation rules for GPS JSON request | 3
|  | Implement JSON validation logic | 8
|  | Validate mapped JSON request against defined rules | 2
| Testing | Write unit tests for XML to JSON mapping and validation | 5
Integration with EMS queue | EMS Queue Setup | Research and choose a suitable JMS library, Configure connection parameters for request and response and statement queue | 4 | 8
|  | Establish connection to the EMS Request queue | 2
|  | Establish connection to the EMS response queue | 2
JMS Publisher (publish message to EMS request queue) | Message Preparation | Retrieve the JSON request data | 1 | 18
|  | Convert JSON request to message format | 2
|  | Set message headers and properties | 1
| Message Publishing | Publish the message to the EMS request queue | 4
|  | Handle message publishing errors and retries | 6
| Testing | Write unit tests for message publishing | 4
Consumer (consume message from EMS response queue) | Message Consumption | Retrieve messages from the EMS response queue | 4 | 30
|  | Handle message deserialization and conversion | 2
|  | Process and validate the received response | 3
|  | Implement message acknowledgment (not sure)and error handling | 12
| Message Processing | Extract relevant data from the response message | 1
|  | Perform necessary transformations or data manipulations | 2
|  | Update application state or trigger further actions(not sure) | ?
| Testing | Write unit tests for message consumption and processing | 4
|  | Update project README with relevant information | 2
|  |  | 148 | 148
Documentation
Document project setup and configuration steps
Document API contracts and payload structures
Document NAS integration process and steps
Document scheduler setup and configuration steps
Document XML to JSON mapping and validation process
Document EMS queue setup and integration process
Document the process of publishing a message to the EMS queue
Document the process of consuming and processing EMS response